ARTI-409-A  |  AI Systems & Governance

AI Operations Control Room

Project Scope & Planning Document

Team Members

Jack  •  Sakir  •  Osele  •  Jeewanjot

Sprint Duration: 4 Weeks  |  Project Weight: 50% of Final Grade

March 2026

Table of Contents

1.  Executive Summary

2.  What We Are Building

2.1  Core Problem & User Story

2.2  The Four Required Modules

3.  Technology Stack & Tools

3.1  Chosen Stack

3.2  Complete Dependency List

3.3  Development Tools & Environment

4.  System Architecture

4.1  High-Level Architecture

4.2  Database Schema Design

4.3  API Endpoint Map

5.  Team Roles & Ownership

6.  4-Week Sprint Plan

6.1  Week 1: Foundation & Service Connection

6.2  Week 2: Monitoring & Evaluation

6.3  Week 3: Incidents & Maintenance

6.4  Week 4: Governance, Polish & Submission

7.  Required Documentation Deliverables

8.  Testing Strategy

9.  Risk Register (Draft v1)

10. Individual Q&A Preparation

11. Production Readiness Checklist

12. Grading Alignment Matrix

# 1. Executive Summary

This document serves as the master project plan for our AI Operations Control Room — a full-stack web application that provides centralized monitoring, evaluation, incident management, and governance for an organization’s AI services. The project is worth 50% of our ARTI-409-A final grade and spans a 4-week sprint with deliverables at Weeks 1, 2, and 4.

Our team of four (Jack, Sakir, Osele, Jeewanjot) will use a React + FastAPI + SQLite stack, connecting to the Anthropic Claude API through a dedicated REST wrapper service layer (llm/client.py) that abstracts all LLM calls behind our own internal API. We will execute the project in Antigravity with a disciplined sprint cadence, maintaining a Prompt & Change Log throughout to satisfy the governance documentation requirement.

Core lifecycle we must demonstrate end-to-end: Monitor → Detect Issue → Create Incident → Triage → Plan Maintenance → Export Compliance Evidence.

A simple, fully working pipeline will score higher than a half-finished application with impressive isolated features. Every decision in this plan optimizes for end-to-end completeness first, polish second.

# 2. What We Are Building

## 2.1 Core Problem & User Story

Organizations deploying AI tools (chatbots, assistants, recommendation engines) lack a single pane of glass to answer: Is the AI working? Has quality drifted? When was it last evaluated? Who approved the last change?

User Story: "As an AI Ops Manager, I need one place to see AI service health, detect quality regressions, schedule maintenance, document incidents, and prove compliance — without exposing sensitive workplace data."

## 2.2 The Four Required Modules

Module 1: AI Service Registry & Connection

A registry to onboard, connect, and health-check AI services. Supports CRUD operations, a "Test Connection" button that pings the LLM and reports latency/status, and enforces that API keys live in backend environment variables only.

- Register services with: name, owner, environment (dev/prod), model name, data sensitivity label (public / internal / confidential)

- Test Connection button → sends prompt, returns latency + success/fail

- Full CRUD for the registry

- Secrets stored in .env on the backend — never in frontend code

Module 2: Monitoring Dashboard & Evaluation Harness

A visual dashboard showing performance metrics per service, plus an evaluation harness that produces quality scores, stores results with timestamps, and flags drift when scores drop below thresholds.

- Dashboard with 3+ metrics per service (latency, error rate, quality score)

- Evaluation harness: manual or scheduled, produces quality score

- At least 2 eval categories (e.g., factuality check, JSON format validation, PII detection)

- Results stored in DB with timestamps, displayed on dashboard

- Drift flag when quality score drops below defined threshold

Module 3: Incident Triage & Maintenance Planner

When quality drops or errors spike, the team creates incidents, runs a guided troubleshooting checklist, and generates LLM-assisted summaries — all requiring human approval before saving.

- Incident creation: service name, severity, symptoms, timeline

- Guided troubleshooting checklist (Data? Prompt? Model? Infra? Safety?)

- LLM-generated incident summary + root cause suggestions — human must approve before save

- Maintenance planner: schedule evaluations, plan update windows

- Update Plan template: risk level, rollback plan, validation steps, human approval checkbox

Module 4: Governance, Security & Compliance

The governance layer that elevates the app from a dashboard to an AI management platform.

- RBAC: Admin, Maintainer, Viewer roles with enforced permissions

- Audit log: every change to endpoints, schedules, incidents, eval settings — timestamped

- Data Handling Policy + Privacy Routing screen: what data is stored, whether prompts are logged, what data leaves the server to Anthropic’s API vs. stays local in SQLite, how sensitivity labels (public/internal/confidential) affect routing decisions, and Anthropic’s data retention policy

- Compliance Evidence Export: downloadable PDF/JSON with eval summaries, incidents, maintenance actions, audit log

# 3. Technology Stack & Tools

## 3.1 Chosen Stack

We are going with Option B from the project outline, optimized for our team’s Python/React skills and the simplicity of SQLite for a 4-week project:

| Layer | Technology | Rationale |
| --- | --- | --- |
| Frontend | React 18 + Vite | Fast dev server, team familiarity, rich ecosystem |
| UI Library | Tailwind CSS + shadcn/ui | Rapid styling, consistent design system |
| Charting | Recharts | React-native charting for dashboard metrics |
| Backend | FastAPI (Python 3.11+) | Async, auto OpenAPI docs, team knows Python |
| Database | SQLite (via SQLAlchemy) | Zero-config, file-based, perfect for demo scope |
| ORM | SQLAlchemy 2.0 + Alembic | Type-safe queries, schema migrations |
| LLM Provider | Anthropic Claude API + REST wrapper | Abstracted behind llm/client.py; easy provider swap |
| Background Jobs | APScheduler | Lightweight scheduler for eval runs + health checks |
| Auth / RBAC | JWT tokens + role middleware | Stateless auth, role checks per endpoint |
| PDF Export | ReportLab or WeasyPrint | Server-side compliance PDF generation |
| Testing | Pytest + React Testing Library | Backend + frontend test coverage |

## 3.2 Complete Dependency List

Backend (Python) — requirements.txt:

fastapi, uvicorn, sqlalchemy, alembic, pydantic, python-jose[cryptography], passlib[bcrypt], httpx, apscheduler, anthropic, python-dotenv, reportlab, pytest, pytest-asyncio

Frontend (Node) — package.json:

react, react-dom, react-router-dom, axios, recharts, @radix-ui/react-*, tailwindcss, lucide-react, date-fns, @testing-library/react, vitest

## 3.3 Development Tools & Environment

- IDE: Antigravity (primary), VS Code as backup

- Version Control: Git + GitHub (branch-per-feature, PR reviews)

- AI Coding Tools: Claude / ChatGPT / Antigravity — all usage logged in Prompt & Change Log

- API Testing: FastAPI built-in /docs (Swagger UI)

- Environment Variables: .env file (git-ignored), loaded via python-dotenv

# 4. System Architecture

## 4.1 High-Level Architecture

The application follows a standard three-tier architecture with a clear separation between the React SPA frontend, the FastAPI backend API, the SQLite database, and an external LLM connection:

[React SPA]  ←→  [FastAPI Server]  ←→  [SQLite DB]

↑↓

[LLM REST Wrapper (llm/client.py)]

↑↓

[Anthropic Claude API]

↑↓

[APScheduler Jobs]

The LLM REST wrapper (llm/client.py) is a dedicated service layer that abstracts all Anthropic SDK calls behind internal functions. No route handler calls the Anthropic SDK directly — all LLM interactions go through this wrapper, making it easy to swap providers (e.g., switch to Ollama or OpenAI) without touching business logic.

Data Flow: User Action → React UI → Axios HTTP call → FastAPI route → SQLAlchemy ORM → SQLite → Response back through chain. For LLM calls: FastAPI route → llm/client.py wrapper → Anthropic SDK → Claude API → response returned to route → displayed in UI for human review → human approves → saved to DB.

## 4.2 Database Schema Design

All tables include id (primary key), created_at, and updated_at fields:

| Table | Key Columns | Purpose |
| --- | --- | --- |
| users | username, email, password_hash, role (admin/maintainer/viewer) | Auth & RBAC |
| ai_services | name, owner, environment (dev/prod), model_name, sensitivity_label ENUM(public/internal/confidential), endpoint_url, is_active | Service registry |
| connection_logs | service_id (FK), latency_ms, status, response_snippet, tested_at | Health check history |
| eval_runs | service_id (FK), quality_score, factuality_score, format_score, drift_flagged, run_type | Evaluation results |
| eval_test_cases | service_id (FK), prompt, expected_output, category | Golden test data |
| incidents | service_id (FK), severity, symptoms, status, timeline, summary, root_causes, approved_by | Incident records |
| maintenance_plans | incident_id (FK), risk_level, rollback_plan, validation_steps, approved, scheduled_date | Update plans |
| audit_log | user_id (FK), action, target_table, target_id, old_value, new_value, timestamp | Governance trail |
| telemetry | service_id (FK), metric_name, metric_value, recorded_at | Dashboard metrics |

## 4.3 API Endpoint Map

All endpoints prefixed with /api/v1. Protected routes require JWT + role check:

| Method | Endpoint | Module | Roles |
| --- | --- | --- | --- |
| POST | /auth/login | Auth | Public |
| POST | /auth/register | Auth | Admin only |
| GET/POST/PUT/DELETE | /services/* | Module 1 | Admin, Maintainer |
| POST | /services/{id}/test-connection | Module 1 | Admin, Maintainer |
| GET | /dashboard/metrics/{service_id} | Module 2 | All roles |
| POST | /evaluations/run/{service_id} | Module 2 | Admin, Maintainer |
| GET | /evaluations/history/{service_id} | Module 2 | All roles |
| GET/POST/PUT | /incidents/* | Module 3 | Admin, Maintainer |
| POST | /incidents/{id}/generate-summary | Module 3 (LLM) | Admin, Maintainer |
| POST | /incidents/{id}/approve-summary | Module 3 | Admin, Maintainer |
| GET/POST/PUT | /maintenance/* | Module 3 | Admin, Maintainer |
| GET | /audit-log | Module 4 | Admin only |
| GET | /compliance/export | Module 4 | Admin only |
| GET | /data-policy | Module 4 (Privacy Routing) | All roles |

# 5. Team Roles & Ownership

Each member owns one primary module but must understand the entire codebase (tested via individual Q&A). Cross-module collaboration is essential at integration points.

| Member | Primary Module | Key Responsibilities | Secondary Support |
| --- | --- | --- | --- |
| Jack | Module 1: Service Registry + Backend Core | FastAPI scaffold, DB schema, SQLAlchemy models, auth/JWT, service CRUD, test connection, .env handling | API routes for all modules |
| Sakir | Module 2: Dashboard + Eval Harness | React dashboard UI, Recharts, eval harness logic, quality scoring, drift detection, APScheduler | Frontend components for all modules |
| Osele | Module 3: Incidents + Maintenance | Incident CRUD, troubleshooting checklist, LLM REST wrapper (llm/client.py) abstracting Anthropic SDK, human approval workflow, maintenance plans | LLM wrapper reused by all modules |
| Jeewanjot | Module 4: Governance + Docs | RBAC middleware, audit log, data handling + privacy routing page, compliance export, all documentation, README | Testing, final polish, presentation |

Critical: Every team member must be able to answer all 5 Q&A questions about the full system. Plan at least 2 cross-module code review sessions in Weeks 3-4.

# 6. Four-Week Sprint Plan

Each week maps to the project outline’s checkpoints. Tasks listed with clear ownership and completion criteria.

## 6.1 Week 1: Foundation & Service Connection (Phase 1 — 10%)

Demo: "Add a service, test the connection, see it stored in the registry."

| Task | Owner | Details | Done When |
| --- | --- | --- | --- |
| Project proposal document | Jeewanjot | Problem statement, architecture diagram, feature plan, model connection plan | Submitted as Phase 1 |
| Risk Register v1 (draft) | Jeewanjot + All | Top 5 risks with planned mitigations | Included in Phase 1 |
| FastAPI project scaffold | Jack | Project structure, routers, DB config, CORS, .env | Server runs, /docs loads |
| SQLite + SQLAlchemy models | Jack | All tables from schema, Alembic migrations | Migrations run clean |
| Auth system (JWT) | Jack | Login/register endpoints, JWT tokens, role field | Can login and get token |
| React project scaffold | Sakir | Vite + React + Tailwind + Router + Axios | App runs, routing works |
| Service Registry UI | Sakir | CRUD form + list view; sensitivity dropdown with exact values: public / internal / confidential | Can add/edit/delete in UI |
| Service Registry API | Jack | CRUD endpoints for /services; sensitivity_label validated as enum | Works via Swagger |
| Test Connection endpoint | Jack + Osele | POST /services/{id}/test-connection routes through llm/client.py wrapper | Returns latency + status |
| LLM REST wrapper (llm/client.py) | Osele | Dedicated service layer wrapping Anthropic SDK; exposes generate_summary(), test_connection(), run_eval_prompt(); no route calls SDK directly | Wrapper tested, provider-swappable |
| Start Prompt & Change Log | All | Shared doc, first entries recorded | Log has initial entries |

## 6.2 Week 2: Monitoring & Evaluation (Phase 2 — 15%)

Demo: "Run an evaluation, score updates the dashboard, drift flag appears when quality drops."

| Task | Owner | Details | Done When |
| --- | --- | --- | --- |
| Telemetry data pipeline | Sakir | Simulated generator or real logging → store → display | Data flows to DB to UI |
| Dashboard UI (3+ metrics) | Sakir | Recharts: latency, error rate, quality score per service | Dashboard shows live data |
| Evaluation harness backend | Sakir + Jack | POST /evaluations/run → runs test cases, scores results | Produces quality score |
| Eval test cases (2 categories) | Sakir + Osele | Factuality checks + JSON format validation | Cases stored in DB |
| Drift detection logic | Sakir | Compare score to threshold → flag drift | Red flag when score drops |
| Eval results storage + display | Sakir | Results in DB with timestamps, on dashboard | Historical runs visible |
| APScheduler integration | Jack | Background job: scheduled health check or eval run | Job runs on interval |
| Evaluation Dataset Card | Jeewanjot | What test data, success criteria, limitations | Phase 2 doc ready |
| Unit tests (5+) | All | At least 5 unit tests across backend | pytest passes all |
| End-to-end integration QA | All | Register → connect → evaluate → dashboard | Full flow works |

## 6.3 Week 3: Incidents & Maintenance

Demo: "Quality drops, create an incident, run the checklist, generate an update plan."

| Task | Owner | Details | Done When |
| --- | --- | --- | --- |
| Incident CRUD API | Osele | POST/GET/PUT /incidents with all required fields | Can create and update |
| Incident creation UI | Osele + Sakir | Form: service selector, severity, symptoms | Incidents in list view |
| Troubleshooting checklist | Osele | Guided wizard: Data? Prompt? Model? Infra? Safety? | Checklist renders, saves |
| LLM incident summary | Osele | Claude drafts summary + root causes | Summary shown for review |
| Human approval workflow | Osele | Approve/reject → only approved saves to DB | Cannot save without approval |
| Maintenance planner UI + API | Osele + Sakir | Schedule evals, plan updates, template form | Plans created and visible |
| Update Plan template | Osele | Risk level, rollback, validation, approval checkbox | Template renders, saves |
| Maintenance Runbook doc | Jeewanjot | If latency > X, if quality < Y, if PII leak | Doc deliverable ready |
| Cross-module integration | All | Wire incidents to eval results and services | Incident links to data |

## 6.4 Week 4: Governance, Polish & Final Submission (Phase 3 — 25%)

Demo: "Viewer role cannot edit, all changes are logged, export the evidence pack."

| Task | Owner | Details | Done When |
| --- | --- | --- | --- |
| RBAC enforcement | Jeewanjot + Jack | Admin (full), Maintainer (CRUD), Viewer (read-only) | Viewer blocked in UI + API |
| Audit log system | Jeewanjot + Jack | Every mutation → audit_log with user, action, timestamp | Changes in audit log page |
| Data Handling + Privacy Routing page | Jeewanjot | Required for cloud LLM: what data goes to Anthropic API vs. stays local, prompt logging policy, how sensitivity labels affect routing, Anthropic data retention | Page in nav, answers all 4 privacy questions |
| Compliance Evidence Export | Jeewanjot | PDF with evals, incidents, maintenance, audit log | PDF downloads with data |
| Integration tests (2+) | All | End-to-end pipeline test + incident-to-export test | pytest passes suite |
| Error handling polish | All | No blank screens, graceful failures, loading states | App handles errors well |
| Final Risk Register | Jeewanjot | Updated with actual mitigations implemented | Final doc submitted |
| Prompt & Change Log final | All | All AI-assisted generation documented | Complete, submitted |
| README with setup instructions | Jeewanjot | Clone → install → env → run | Someone else can run it |
| Presentation prep | All | Demo script, Q&A practice, architecture walkthrough | Team rehearsal done |
| Production readiness check | All | All checklist items verified | Checklist signed off |

# 7. Required Documentation Deliverables

These are graded deliverables. Missing any will lose marks under the documentation category (3% of Phase 3).

| Document | Description | Due | Owner |
| --- | --- | --- | --- |
| Prompt & Change Log | Every major AI-assisted code generation: goal, prompt, what changed, verification | Ongoing (with final) | All (Jeewanjot maintains) |
| Model Risk Register | Top 5 risks + mitigation controls implemented in the tool | v1 Phase 1, final Phase 3 | Jeewanjot + All |
| Evaluation Dataset Card | Test data used (synthetic), success criteria, known limitations | Phase 2 | Sakir + Jeewanjot |
| Maintenance Runbook | Operational playbook for latency, quality drops, PII leaks | Phase 3 | Jeewanjot + Osele |

# 8. Testing Strategy

Minimum requirement: 5 unit tests + 2 integration tests. Our target is 8+ unit and 2 integration tests.

Unit Tests (target 8):

- test_create_service: Service registration creates correct DB record

- test_test_connection: Mock Claude API, verify latency calculation and status

- test_eval_scoring: Evaluation harness produces correct quality score

- test_drift_detection: Drift flag triggers when score below threshold

- test_incident_creation: Incident CRUD and field validation

- test_rbac_viewer_blocked: Viewer role rejected from mutation endpoints

- test_audit_log_entry: Mutations create audit records with correct metadata

- test_jwt_auth: Token generation, validation, and role extraction

Integration Tests (2):

- test_full_eval_pipeline: Register → evaluate → check dashboard → verify drift flag

- test_incident_to_export: Create incident → generate summary → approve → export PDF → verify contents

# 9. Risk Register (Draft v1)

Initial draft for Phase 1 submission. Will be finalized in Phase 3 with actual implemented controls.

| # | Risk | Likelihood | Impact | Mitigation in Our Tool |
| --- | --- | --- | --- | --- |
| 1 | Data Privacy Breach: sensitive data sent to cloud LLM | Medium | High | Sensitivity labels (public/internal/confidential) on every service, dedicated Privacy Routing page explaining what data leaves server to Anthropic API vs. stays local, LLM calls abstracted through REST wrapper for provider-swap capability |
| 2 | Model Drift: quality degrades silently over time | High | High | Eval harness with scheduled runs, drift flag, dashboard visibility |
| 3 | Hallucination: LLM generates inaccurate summaries | High | Medium | Human-in-the-loop: all LLM outputs require approval before saving |
| 4 | Bias in AI Outputs: biased root cause suggestions | Medium | Medium | Human review, audit log of approvals, policy adherence eval tests |
| 5 | Service Outage: LLM provider goes down | Medium | Medium | Health checks, error handling, incident workflow works without LLM |

# 10. Individual Q&A Preparation

Every team member faces these 5 questions during a 2-minute individual session. Prepare answers regardless of your primary module.

| # | Question | What to Know | Where in Code |
| --- | --- | --- | --- |
| 1 | Walk through the architecture and data flow | React → Axios → FastAPI route → SQLAlchemy → SQLite. LLM calls go through llm/client.py REST wrapper → Anthropic SDK → Claude API. No route touches SDK directly. | main.py, llm/client.py, models.py, App.jsx |
| 2 | How does the eval harness work? What happens on quality drop? | Test cases sent via llm/client.py wrapper, scored vs expected, stored, if < threshold → drift flag → dashboard red indicator | evaluations/router.py, Dashboard.jsx |
| 3 | Show the audit log. Where is a model endpoint change recorded? | Every mutation → audit_log with user, action, target, old/new, timestamp | middleware/audit.py, AuditLog.jsx |
| 4 | Where is LLM called? What prevents auto-approve? | All LLM calls go through llm/client.py wrapper (never raw SDK in routes). Response shown in UI, user must click Approve before DB write. | llm/client.py, incidents/router.py, IncidentSummary.jsx |
| 5 | Biggest risk with confidential data? How do we address it? | Data leakage to cloud LLM. Mitigated by: sensitivity labels (public/internal/confidential), privacy routing page explains what leaves server, RBAC, audit trail | Privacy routing page, RBAC middleware, llm/client.py |

# 11. Production Readiness Checklist

Pass/fail requirements to verify before final submission:

| # | Requirement | How to Verify | Status |
| --- | --- | --- | --- |
| 1 | No API keys in frontend or git history | grep -r ANTHROPIC frontend/ + check .gitignore | Pending |
| 2 | Error states handled, no blank screens | Test: disconnect DB, bad API key, network failure | Pending |
| 3 | Viewer cannot do Admin/Maintainer actions | Login as Viewer, try mutations → all blocked | Pending |
| 4 | Eval results are reproducible | Run eval twice → consistent scores | Pending |
| 5 | Compliance export generates with real data | Click Export → PDF downloads with actual data | Pending |
| 6 | README has working setup instructions | Fresh clone, follow README → app runs | Pending |
| 7 | Prompt & Change Log is complete | Review → 10+ entries with goals/prompts/changes | Pending |

# 12. Grading Alignment Matrix

Every grading criterion mapped to specific tasks in our plan to ensure nothing is missed:

Phase 1: Project Proposal (10%)

| Criteria | Weight | Our Deliverable |
| --- | --- | --- |
| Problem Statement | 2% | Proposal doc Section 1 |
| Architecture & Data Flow | 3% | Architecture diagram with all components + data flow |
| Feature Plan | 2% | This document: Sections 2 + 6 |
| Model Connection Plan | 1.5% | Claude API via REST wrapper (llm/client.py), privacy routing page documents cloud data flow |
| Risk Register v1 | 1.5% | Section 9, expanded in standalone doc |

Phase 2: Midterm Progress (15%)

| Criteria | Weight | Our Deliverable |
| --- | --- | --- |
| Working Model Connection | 3% | Test Connection button → routed through llm/client.py wrapper → Claude responds with latency |
| Monitoring Dashboard | 4% | Recharts dashboard: latency, error rate, quality score |
| Evaluation Harness | 4% | Manual + scheduled eval, quality score, drift flag |
| Code Quality & Tests | 2% | 5+ unit tests, Prompt & Change Log started |
| Team Progress | 2% | All members contributing, architecture matches proposal |

Phase 3: Final Submission & Presentation (25%)

| Criteria | Weight | Our Deliverable |
| --- | --- | --- |
| Full Workflow Demo | 6% | Monitor → Detect → Incident → Triage → Maintain → Export |
| Governance & Security | 4% | RBAC, audit log, data handling + privacy routing page, compliance export |
| Code Quality & Reliability | 3% | 5 unit + 2 integration tests, error handling, README |
| Documentation Package | 3% | Prompt log, risk register, eval dataset card, runbook |
| Group Presentation | 5% | Clear demo, all members present, architecture explanation |
| Individual Q&A | 4% | Each member prepared for all 5 questions (Section 10) |

End of Project Plan  —  AI Ops Control Room  —  ARTI-409-A